## Execution Plan ,Soho Editors Training

Scope: training only. PayPal stays. Tutorials stay on Vimeo OTT as outbound links. Bookings, scheduling, payments, and admin move in-house.

### Phase 0 ,Discovery (do not skip)

You cannot design the schema until this is done.

- Inventory Kahuna. Every content type, every field, every dropdown. This is your catalogue schema, handed to you free.

- Get the SQL dump + uploads folder. Not to migrate ,to count and inspect. How many courses, sessions, orders, users? What do the meta fields actually contain?

- Get the Pencil Me In walkthrough. He's explaining it. Record it. It's a state machine and you need every state.

- Resolve bundles / rewards / guarantee. Live or dead. Written answer.

- Trace one real booking end to end. Cart → PayPal → confirmation email → what the team sees → what the customer sees. Screenshot every step. That's your commerce spec.

Output: a field-level content inventory + a booking flow diagram. Nothing else starts until these exist.

### Phase 1 ,Foundation

- Postgres schema (below), migrations, seed data.

- FastAPI skeleton, auth, roles, admin scaffolding.

- Next.js skeleton, component library from Figma.

- AWS: RDS, S3, EC2/App Runner, CloudFront.

- PayPal sandbox wired up early. Do not leave payments to the end ,it's the thing most likely to surprise you.

### Phase 2 ,Catalogue & Admin (the boring half ,build it first)

This is most of the 9 pages and most of Kahuna.

Entities:

| Entity | Notes |
| --- | --- |
| Software | Premiere, After Effects, Resolve… ,the taxonomy everything hangs off |
| Skill | Tagging for courses and trainers |
| Course | Overview, objectives, outline, level, duration, price, trailer, images. Price lives here (per your answer) |
| Session | A dated instance of a course. Date, duration, mode (classroom / live online), location, price override. This is what goes in the cart |
| Trainer | Profile, bio, specialities, linked software |
| Testimonial | Written + YouTube video variants |
| Resource | Free downloads ,templates, manuals, funding guides. S3 files |
| FreeTutorial | YouTube embed |
| ProTutorial | Title, trailer, price, outbound Vimeo OTT URL. No entitlement logic. Just a link |
| Page | Generic page for bespoke landing pages |
| Settings | Tracking codes, GA, verification tags |

Admin CRUD for every one of the above. This is the CMS replacement, and it's what the client will judge you on daily.

Public pages this unlocks: Training Home, Courses, Course Detail, Our Trainers, Resources, Free Tutorials, Reviews, Certified Pro Tutorials.

### Phase 3 ,Accounts & Registration

- Guest checkout must work. Orders exist without users. Design for this from the start ,it's a foreign key that's nullable, and retrofitting it is painful.

- Registration, login, email verification, password reset.

- User migration: WordPress hashes are bcrypt/phpass. If you build auth in FastAPI you can verify against the existing hashes directly ,no forced reset, no friction. This is a strong argument for FastAPI-native auth over Cognito. Take it.

- Roles: customer, trainer, admin.

- My Profile / My Bookings ,the site already has a "My Profile" nav item and "Change my Booking". Customers can view bookings and request timing changes (per your answer 12).

### Phase 4 ,Cart, Booking & Payments (the risk)

Build in this order:

- Cart. Server-side, session-backed so guests work. Line item = a Session + attendee details + type (paid | pencil).

- Multi-seat = same session added N times. Per your answer 11. Crude, but it's what they do ,match it.

- Attendee capture. Per line item. Optional; defaults to purchaser.

- Coupon codes. Cart-level. Percentage or fixed, expiry, usage cap.

- VAT. 20%, itemised as its own line. Subtotal / VAT / discount / total, exactly as the current checkout shows.

- Pencil Me In. Zero-cost line item, coexists with paid items in one cart. Produces a booking in pencilled state. Needs admin tooling to confirm or release. Spec this from the client's walkthrough before you build it.

- PayPal checkout. Orders API, webhooks for confirmation, guest-friendly. Pay in 3 comes free with PayPal ,that's a reason you're keeping it.

- Orders & confirmations. Order record, email receipt, joining instructions.

Admin side: view carts and sales (he explicitly asked), manage bookings, confirm/release pencils, issue refunds.

### Phase 5 ,Bespoke Training

Trivial by comparison. Form → enquiry record → admin inbox → email notification. Do it in an afternoon.

### Phase 6 ,Migration

- Users (with hashes preserved ,see Phase 3).

- Courses, sessions, trainers, testimonials, resources.

- Media → S3, references rewritten.

- Historical orders: ask if he needs them. If yes, it's a real job. If archive-only, dump them in a read-only table and move on.

- 301 redirects, sitemap, SEO metadata.

### Phase 7 ,QA & Launch

- Full booking flow tested in PayPal sandbox, then live with a real £1 transaction.

- VAT arithmetic verified against real invoices.

- Pencil workflow tested with the actual bookings team.

- Redirects verified against the old sitemap.

- WordPress kept warm as rollback for a week.

### Build order, one line

Catalogue → Accounts → Cart → Payments → Pencil → Bespoke → Migration → Launch.

Catalogue first because everything else reads from it and the migration lands into it. Payments before Pencil because Pencil is a variant of the cart, not a separate thing. Migration late because the schema must be stable first.

### The three things most likely to hurt you

- Pencil Me In. Undocumented, human-in-the-loop, and it's in the cart. Get the full flow in writing.

- PayPal edge cases. Failed payments, abandoned carts, webhook replays, guest orders that never complete. Budget real time.

- The SQL dump. WordPress postmeta is a swamp. You won't know how bad until you open it. Open it early.

### One thing to hold firm on

Give him rich text for those content fields, not raw HTML, and not a page builder. A constrained editor ,headings, bold, lists, links ,rendered into your fixed layout. The moment you give him an HTML field he will paste in styled markup from Word and your design will break within a month.

If he pushes for "but I want a different layout for this one course" ,that's the request that turns a structured CMS into a page builder. Say no once, clearly, now.

The line you're drawing

| Page type | Who owns it | How it's edited |
| --- | --- | --- |
| Static pages ,Training home, Our Trainers, Resources, Free Tutorials, Reviews, Live Online, Bespoke, Certified Pro | You. Layout is fixed, coded in Next.js | Dev deploy |
| Dynamic pages ,Course detail | Admin. Content comes from Course | CMS, no dev |

But the static pages still show CMS data. Our Trainers is a fixed layout rendering a dynamic list of trainers. Same for Resources, Free Tutorials, Reviews, Certified Pro. So admin still CRUDs trainers, testimonials, resources, tutorials ,he just can't change the layout of the page they appear on. Make sure the client understands that distinction, because "static" will make him think he can't add a trainer.